## PR Copilot Roadmap
Phase | Priority | Task | Goal | Files / Areas | Why It Matters | Estimated Effort | Status | Dependencies | Definition of Done
Security Foundations | 1 | Server-side auth verification | Verify Supabase user server-side in API routes | pages/api/evaluate.ts, pages/api/generate.ts | Prevents spoofed user_id abuse | 1-2 days | Not Started | Supabase JWT/session access | Authenticated user verified in both API routes
Security Foundations | 2 | Remove client user_id trust | Use authenticated Supabase user ID only | pages/api/evaluate.ts, pages/api/generate.ts | Stops malicious impersonation | 0.5 day | Not Started | Task 1 | No client-provided user_id used anywhere
Security Foundations | 3 | Database-backed usage tracking | Move 5-free-pitch logic to Supabase | Supabase schema, pages/api/generate.ts | Current limit is bypassable | 1-2 days | Not Started | Tasks 1-2 | Usage tied to authenticated account
Security Foundations | 4 | Add API abuse protection | Rate limits and request size limits | API routes | Controls OpenAI cost exposure | 1 day | Not Started | Tasks 1-3 | Large or abusive requests blocked
Security Foundations | 5 | Remove debug payloads | Hide raw model responses in production | pages/api/evaluate.ts | Reduces exposure of internal logic | 0.5 day | Not Started | None | No raw parsed output returned publicly
Database & Auth | 6 | Implement Supabase RLS policies | Restrict user access to own records | Supabase | Critical for production security | 1 day | Not Started | Tasks 1-3 | Users can only access their own evaluations
Database & Auth | 7 | Improve persistence handling | Surface DB failures cleanly | API routes + frontend | Current failures are hidden | 1 day | Not Started | Tasks 1-6 | User sees actionable error states
Frontend UX | 8 | Remove client-side pitch state | Stop using local React state for usage | pages/index.tsx | Current usage logic is fake | 0.5 day | Not Started | Task 3 | Frontend reads usage from DB
Frontend UX | 9 | Redesign evaluation experience | Premium editorial UX without visible scoring | pages/index.tsx | Current UI damages credibility | 2-4 days | Not Started | Tasks 1-8 | Apple-quality clean evaluation experience
Frontend UX | 10 | Improve auth/account UX | Add logout, account state, onboarding | pages/index.tsx | Current auth flow is minimal | 1-2 days | Not Started | Task 1 | Users clearly understand account state
Frontend UX | 11 | Improve history UX | Better saved evaluations and generations | pages/index.tsx | Current history is shallow | 1-2 days | Not Started | Persistence stable | Users can browse prior work cleanly
Production Readiness | 12 | Add schema validation | Validate API request bodies | API routes | Avoid malformed requests | 1 day | Not Started | Tasks 1-4 | All requests validated before processing
Production Readiness | 13 | Add linting and build checks | Ensure stable deploy pipeline | package.json, CI setup | Prevents broken deploys | 0.5 day | Not Started | None | Lint/build pass before deployment
Production Readiness | 14 | Add tests | Basic API and auth coverage | API routes | Critical for future iteration | 2-3 days | Not Started | Core auth complete | Smoke tests passing
Production Readiness | 15 | Verify Vercel deployment | Production deployment configuration | Vercel + Supabase OAuth | App currently local-first | 1 day | Not Started | Tasks 1-14 | Stable production deployment
Business Layer | 16 | Stripe/payment integration | Introduce paid plans | Frontend + backend + Stripe | Core monetisation layer | 2-4 days | Not Started | Usage tracking complete | Users can upgrade and pay
Business Layer | 17 | Pricing and onboarding flow | Clarify free vs paid product | Frontend | Current positioning unclear | 1-2 days | Not Started | Stripe integration | Clear upgrade path exists
Business Layer | 18 | Analytics and tracking | Measure user behaviour | Frontend + backend | Needed for iteration | 1 day | Not Started | Production deployment | Basic product analytics working

## Execution Order
Sprint | Focus | Deliverables | Outcome
Sprint 1 | Security & Auth | Server-side auth, remove user_id trust, RLS | Safe public foundation
Sprint 2 | Usage & Abuse Protection | DB-backed limits, rate limiting, validation | Controlled OpenAI cost and access
Sprint 3 | Persistence & Reliability | Better error handling, stable history | Reliable user experience
Sprint 4 | Premium UX | Editorial redesign, auth/account polish | Credible founder-facing product
Sprint 5 | Production Launch | Vercel deploy, tests, linting | Stable deployable MVP
Sprint 6 | Monetisation | Stripe + onboarding | Revenue-ready product