## Roadmap (Step-by-step)
Priority | Phase | Task | Why it matters | How to do it (steps) | Owner | Status | ETA | Dependencies | Definition of Done
P0 | Stabilize Core | Connect Supabase end-to-end (Auth + DB + RLS) | Without this, you can’t reliably identify users, enforce limits, or store history. It’s the backbone. | 1) Confirm Supabase project URL + anon key in .env.local 2) Install libs: @supabase/supabase-js and (optional) @supabase/auth-helpers-nextjs 3) Create /lib/supabaseClient.ts (browser) + /lib/supabaseServer.ts (server) 4) Configure Auth: GitHub provider + Site URL + Redirect URLs 5) Create tables: profiles, usage, generations (optional) 6) Enable RLS + policies for each table 7) Update UI to show session state + sign-in/sign-out 8) Test login, token persistence, DB reads/writes | Chris | Not started | 1–2 days | Supabase project created | Login works, session persists, DB tables exist, RLS on, app can read/write usage for logged-in user
P0 | Stabilize Core | Fix generation route: server-side OpenAI call + robust error handling | If /api/generate is flaky, users think the product is broken. Also prevents key leakage. | 1) Ensure OpenAI key is ONLY used server-side 2) In /api/generate: validate input + auth 3) Add try/catch with clear JSON errors 4) Handle 429/insufficient_quota with user-facing message 5) Log request_id for debugging | Chris | Not started | 0.5 day | Supabase auth working | Generate returns output reliably; errors show cleanly; no key exposed to client
P0 | Stabilize Core | Enforce free-tier limits in DB (not in-memory/UI) | Limits must survive refresh, device changes, and be enforceable for billing later. | 1) Decide limit window: monthly (recommended) or rolling 30 days 2) usage table: user_id, period_start, count 3) In /api/generate: read usage for user & period 4) If count >= limit, block and return 'upgrade' error 5) Otherwise increment usage in a transaction/RPC | Chris | Not started | 0.5–1 day | Supabase tables + RLS | Usage decrements correctly; hitting limit blocks server-side
P1 | Product Wedge | Implement the 'First PR Shot' validator (newsworthiness + credibility gaps + go/no-go) | This is your differentiation from 'ChatGPT for press releases'. It’s judgment, not writing. | 1) Add a new flow: /validate 2) Structured inputs: what, why now, proof, audience 3) Server route calls model with rubric 4) Output: verdict, risks, missing proof, best angles (ranked) 5) Save result to DB for user history | Chris | Not started | 2–4 days | Stable generate + auth | User can run validator, gets structured output, saved to history
P1 | UX/Polish | Upgrade UI to premium editorial (landing + app shell + components) | Trust is visual. If it looks cheap, founders assume outcomes are cheap. | 1) Add AppShell layout (header, nav, footer) 2) Use Tailwind + a small component set (shadcn/ui) 3) Add loading states, toast errors, copy-to-clipboard 4) Add 'Why not just use ChatGPT?' section on landing + FAQ 5) Add clear CTA: Validate first PR shot | Chris | Not started | 2–3 days | Core flows stable | Looks credible on mobile/desktop; smooth flows; clear differentiation copy
P1 | Data/Signal | Basic outcomes tracking (signals, not perfect attribution) | Helps retention: you show momentum. You don’t need perfect ROI yet. | 1) Track: generated items, validator runs, saved outputs 2) Optional: let users log coverage URLs 3) Show dashboard: activity + 'next best action' 4) Add email 'weekly summary' later | Chris | Not started | 1–2 days | DB history tables | Dashboard shows usage + saved outputs; user can log coverage
P2 | Go-to-market | Founder acquisition loop (10 interviews + 3 pilot users) | You need proof people pay for judgment and de-risking, not copy generation. | 1) Recruit 10 founders (your network) 2) Run 20-min calls with a script 3) Give them access, watch them use it 4) Ask: what would you pay? what would replace agency work? 5) Capture quotes (permission-based) | Chris | Not started | 1–2 weeks | Validator flow live | 10 interviews done, 3 active pilots, pricing signal gathered
P2 | Monetization | Add Stripe paywall (Pro = unlimited or higher limit) | Revenue validates willingness-to-pay and funds scaling. | 1) Stripe account + product/price 2) Create checkout session route 3) Webhook updates user plan in Supabase 4) Gate features by plan 5) Upgrade flow when limit hit | Chris | Not started | 2–4 days | DB usage enforced | Paid users upgrade, plan stored, limits expand
P3 | Scale | Journalist relevance scoring + safe contact suggestions | This adds execution value without becoming a spam cannon. | 1) Start with outlet-type recommendations 2) Add optional curated lists per niche 3) Add 'do not contact' guardrails 4) Add templates for outreach timing | Chris | Not started | 2–6 weeks | Traction + clear legal posture | Users get safer targeting guidance; reduced spray-and-pray

## Runbook (Test MVP)
Step | What you do | Expected result | If it fails, check
1 | Open project folder in VS Code (or your editor). | You can see /pages (or /app), /lib, /api routes. | Wrong folder / wrong unzip
2 | Confirm .env.local exists in project root. | Contains NEXT_PUBLIC_SUPABASE_URL, NEXT_PUBLIC_SUPABASE_ANON_KEY, OPENAI_API_KEY (and service role if used server-side). | .env.local in wrong folder; typos; missing quotes; needs server restart
3 | Start dev server: `npm install` then `npm run dev`. | Local site loads at http://localhost:3000 | Node/npm not installed; terminal path wrong; package-lock issues
4 | Visit the site in a clean browser profile (or Incognito). | No extension interference; UI loads. | Wallet/security extensions injecting scripts
5 | Click Sign in (GitHub). | Redirect to GitHub, then back; user email appears in UI. | Supabase provider not enabled; redirect URLs wrong; Site URL mis-set
6 | Run a test generation. | Spinner, then output appears; usage decreases. | API 500 -> check server console; OpenAI billing/quota; route code errors
7 | Hit the free limit (e.g., 5). | Server returns 'limit reached' and UI shows upgrade CTA. | Limit enforced only client-side; DB/RLS misconfigured
8 | Refresh page; repeat generation. | Usage persists across refresh (DB-backed). | Usage stored only in state/localStorage
9 | Sign out; sign back in. | User session resets correctly; usage is still correct for that user. | Auth helpers misconfigured; cookies/localStorage blocked
10 | Check Supabase tables (usage/generations). | Rows exist for your user and update per action. | RLS blocking inserts/selects; wrong user_id mapping

## Founder Positioning
Principle | What it means | Action you take | Risk if you ignore
Be the product, not the personality | You can stay low-profile if the product delivers judgment and confidence. | Use company-led content (case studies, templates, benchmarks). Keep personal posting minimal. | If you hide AND the product looks generic, you’ll look like 'a prompt pack'.
Borrow credibility | Founders buy credibility insurance. You can borrow it via partners, not personal branding. | Go through accelerators/VCs/communities; secure 2–3 endorsements; use permissioned quotes. | Without borrowed trust, conversion will be slow.
Use a 'Chief of Staff' brand voice | Write as the calm operator, not the influencer. | Website + onboarding copy should sound like a senior comms strategist: concise, decisive, critical. | If you sound hypey, you trigger skepticism immediately.
Avoid founder-as-sales | You don’t need to be a public figure; you do need distribution. | Do 10 founder interviews privately; close pilots quietly; ask for intros. | If you rely on public persona, you’ll burn energy you don’t have.
Productized 'No-Go' decisions | Trust comes from saying 'don’t do PR yet' with reasons. | Make Go/No-Go a first-class feature; show credibility gaps and required proof. | If you only say yes, users assume it’s shallow AI.
Define a public face option | If needed later, hire/contract a spokesperson for marketing. | Plan: you remain product/strategy; spokesperson runs content + webinars. | If you delay this forever, growth may stall once pilots end.

## Costs (Start → Scale)
Cost Item | Early (per month) | Scale (per month) | Notes
Vercel hosting | 20 | 100 | Early: hobby/pro. Scale: higher bandwidth, more functions.
Supabase | 0 | 200 | Early: free tier. Scale: db size, auth MAU, backups.
OpenAI API | 100 | 3000 | Driven by usage. Use caps; optimize prompts; add caching.
Logging/Monitoring (Sentry, etc.) | 0 | 100 | Optional early; important at scale.
Email (MailerLite/ConvertKit) | 0 | 150 | Free early; scale with subscribers.
Domain + DNS | 1 | 1 | Annual cost averaged monthly.
Design/Brand | 0 | 500 | You can DIY early; later pay for polish.
TOTAL |  |  | Rough order-of-magnitude