## Overview
PR Copilot — Live Deployment & Next Steps Plan
Current position |  | Plan logic
Real repo path | /Users/chris-air/Projects/pr-copilot-mvp | Goal | Get a narrow, public-safe MVP live first; then add persistence and depth.
GitHub repo | https://github.com/sealax/pr-copilot-mvp | Public scope | Landing page + evaluation form + verdict/risk output. Generation limited or marked experimental.
Local build | Passes (`npm run build`) | Why | A live URL proves shipping. Persistence and polish come immediately after.
Local app | Working locally with PR readiness evaluation + GitHub auth | Recommended framing | Prototype AI tool for evaluating PR readiness before media outreach.
Core risk right now | Still no live URL, no persistence, prototype UI
Status summary |  | Recommended sequence
Status | Count | 1. Deploy narrow prototype to Vercel
Done | 0 | 2. Remove or hide fragile public features
In progress | 0 | 3. Add persistence for evaluations + generations
Next | 6 | 4. Enforce server-side limits in DB
Later | 10 | 5. Improve design and output UX
Blocked | 0 | 6. Add differentiated PR judgement features

## Roadmap
Priority | Workstream | Task | Why it matters | Immediate next action | Current state | Status | Target timing | Dependencies | Definition of done
P0 | Deploy | Public-safe scope decision | Reduces risk of showing half-built features live. | Hide or disable public generation; keep evaluation as the hero. | Decision agreed in principle; not implemented yet. | Next | Today | Local repo stable | Public demo shows only stable features, labeled as prototype.
P0 | Deploy | Prototype disclaimer + honest copy | Interview-safe framing matters more than polish. | Add 'Prototype for demonstration purposes' and state generation is limited/experimental. | Not added yet. | Next | Today | Public-safe scope decision | Landing page and app clearly frame the demo honestly.
P0 | Deploy | Vercel project import from GitHub | This creates the live URL and preview deploys. | Import sealax/pr-copilot-mvp into Vercel. | Local build passes; repo pushed; Vercel import paused before config. | Next | Today | Repo on GitHub | Project exists in Vercel and is linked to main branch.
P0 | Deploy | Production env vars in Vercel | Without correct env vars the live app will fail. | Add OpenAI and Supabase env vars in Vercel project settings, then redeploy. | Working locally only. | Next | Today | Vercel project created | Production deployment can authenticate and evaluate.
P0 | Deploy | Smoke test production deployment | You need proof the public URL actually works. | Test homepage, evaluation, auth, and failure handling on live URL. | Not started. | Next | Today | Production env vars added | Live URL works on desktop/mobile with no blocker-level bug.
P1 | Persistence | Create DB-backed persistence for evaluations | Without history the product still feels like a toy. | Design tables for profiles, evaluations, generations, usage. | Not built. | Next | 1–2 days after deploy | Supabase project working | Users can revisit saved evaluations.
P1 | Persistence | Save evaluation results to Supabase | This is the first meaningful persistence feature. | On successful /api/evaluate, insert row linked to user. | Not built. | Later | 1–2 days after schema | Persistence schema | Each evaluation is written and can be fetched later.
P1 | Persistence | Save generations to Supabase | Needed if generation remains in product and to support history/export. | On successful /api/generate, insert generation row linked to evaluation/user. | Not built. | Later | 1–2 days after schema | Persistence schema | Generated outputs are stored and retrievable.
P1 | Persistence | Enforce free-tier limits server-side in DB | Client-side limits are not credible or billable. | Move usage counting to DB/RPC and block in API route. | Local/demo-style counter only. | Later | 2–3 days | Usage table + auth | Limits survive refresh, new browser, and new device.
P1 | Functionality | History/dashboard page | Persistence only matters if users can see it. | Add 'History' or dashboard route listing prior evaluations/generations. | Not built. | Later | 2–4 days | Persistence implemented | Logged-in user can view prior runs.
P1 | Functionality | Improve evaluation output structure | The current evaluator works, but the UI can communicate judgment better. | Add clearer sections: verdict, evidence gaps, journalist reaction, next actions. | Logic exists; UI basic. | Later | 2–3 days | Core flow stable | Output is skimmable and presentation-ready.
P1 | Design | Editorial premium UI pass | Trust is visual; current UI undersells the work. | Introduce clean app shell, stronger typography, spacing, and CTA hierarchy. | Not done; desired style defined (editorial, premium, light, Apple-like). | Later | 3–5 days | Core live demo stable | Interface looks credible on mobile and desktop.
P1 | Design | Public landing page with stronger positioning | Explains why the tool exists and why not just use ChatGPT. | Add sections: what it does, why it matters, why not just use ChatGPT, prototype note. | Not done. | Later | 2–3 days | Prototype disclaimer | Landing page explains wedge clearly and honestly.
P2 | Differentiation | First PR Shot validator / PR-readiness wedge | This is the defensible product layer beyond generic generation. | Turn evaluation into the hero feature with stronger rubric and named evidence gaps. | Partially there already; needs productization. | Later | 1–2 weeks | Persistence + design | Users see clear PR judgment, not just text generation.
P2 | GTM | Private pilot interviews (5–10 founders / PR users) | You need validation on willingness to pay and feature value. | Run calls, observe usage, capture quotes and objections. | Not started. | Later | 1–2 weeks after live demo | Live URL | At least 5 interviews completed and feedback captured.
P2 | Monetization | Stripe/paywall for pro tier | Do not add this before DB-backed limits and persistence. | Add upgrade flow after limit hit and sync plan to Supabase. | Not started. | Later | After persistence | Server-side limits enforced | User can upgrade and plan state changes correctly.

## Deployment Checklist
Deploy PR Copilot — Minimum public-safe checklist
Rule | Deploy a narrow, stable demo. Do not expose messy features just because they exist locally.
Recommended live scope | Landing page + evaluation form + verdict/risk output. Generation limited, hidden, or labeled experimental.
Reason | A live URL proves shipping. A broken 'full product' undermines the signal.
Step | Checklist item | Owner | Status | Notes
1 | Import GitHub repo into Vercel | Chris | Next | Use GitHub integration, not manual ZIP deploy.
2 | Add production env vars | Chris | Next | OpenAI + Supabase values must be in Vercel settings.
3 | Redeploy after env vars | Chris | Next | Env changes require a new deployment to take effect.
4 | Confirm production homepage loads | Chris | Next | No blank page, no auth crash, no broken placeholder copy.
5 | Run one public-safe evaluation test | Chris | Next | Use a sample input that reliably produces a meaningful verdict.
6 | Check auth path (if public login is required) | Chris | Later | If auth is flaky, do not force it for the public demo.
7 | Check mobile layout | Chris | Later | At least basic credibility on phone.
8 | Add prototype note to page | Chris | Next | Protects you in interviews and keeps the framing honest.
9 | Add live URL to CV/LinkedIn/GitHub README | Chris | Later | Only once the demo is stable.

## Persistence Plan
Persistence plan — what to build first
Priority | Table / Feature | Core fields | Why | API / UI touchpoint | Status | Suggested order | Definition of done
P1 | profiles | id, email, plan, created_at | Basic user record and plan state. | Auth/session initialization | Later | 1 | User exists in DB and can be referenced safely.
P1 | evaluations | id, user_id, inputs, verdict, score, breakdown_json, reaction, recommendation, created_at | This is the real value artifact. | /api/evaluate write + history page read | Next | 2 | Each successful evaluation is stored and fetchable per user.
P1 | generations | id, user_id, evaluation_id (nullable), prompt, output, created_at | Lets users return to prior drafts and supports export later. | /api/generate write + history page read | Later | 3 | Each successful generation is stored and linked if appropriate.
P1 | usage | user_id, period_start, eval_count, generation_count, plan | Needed for enforceable limits. | API routes only | Later | 4 | Server-side checks survive refresh/device changes.
P1 | history UI | list of prior evaluations/generations | Makes persistence visible and useful. | New dashboard/history route | Later | 5 | User can browse previous work without DB console.

## Open Decisions
Open decisions to settle before expanding scope
Decision | Recommended answer | Why | Owner | Status | When to decide
Public demo includes generation? | No, or only as clearly experimental. | Evaluation is the stronger, safer interview demo. | Chris | Next | Before Vercel deploy
Require auth for public demo? | Prefer no for evaluation demo if auth adds friction. | Friction kills credibility faster than limited scope. | Chris | Next | Before Vercel deploy
Usage limit window | Monthly, DB-backed. | Easier to explain and monetize. | Chris | Later | Before persistence launch
Primary wedge | PR readiness / go-no-go judgment. | Stronger answer to 'why not just use ChatGPT?'. | Chris | Later | During design + copy pass
First paid tier | £29/mo Pro after free limited usage. | Reasonable wedge price if the product saves time and improves judgment. | Chris | Later | After pilots + DB limits